EC-Eumetcal-03 : IMPLEMENTATION PLAN – Sept 06 to Feb 07

# IMPLEMENTATION PLAN – Sept 06 to Feb 07

## Introduction

Now that we have permission to go ahead with some aspects of the plan, we need to move quickly to achieve the early goals. However, we are not allowed to have a centralised administration for the College and so must develop a de-centralised system. This plan lists the critical phases necessary to start the programme and allocates responsibility within the framework of the existing Eumetcal Programme. Items not on the critical path can be left until later to implement. Implementation plan 2 can be developed to run from about February 07 and can include the later training courses.

## Implementation Plan Sept 06-Feb 07   Ver 1.0.

| Action | Notes | Date due | Responsible |
| --- | --- | --- | --- |
| Aviation course development |  |  |  |
| Contact COMET | Note 1 | Mid October | Christophe |
| Fix syllabus |  | End October | Christophe |
| Develop course material | Note 2 | 1st week of material by mid November Remainder in sequence | Christophe |
| Review material and teachers/ make links with NMSs wishing to help Assist in seeking comments From NMSs | Note 3 | As required | Christophe Jaakko |
| Contact BoM | Note 1 | As required | Christophe/ Vesa |
| Support for course delivery |  |  |  |
| Develop web site | Note 4 | End November | Jaakko |
| Course delivery software | Note 5 | End November | Jaakko / Laurent |
| Acquiring the appropriate number of suitable students | Note 6 | Mid December | Christophe |
| Preliminary work on NMS course | Note 8 | February 07 | Vesa |
| Contact with MET Alliance | Note 9 | November | Carola |
| Arrange for local tutors |  | By end December at latest (start work in October) | Christophe |
| ### Competency Examination | Note 7 |  |  |
| ### Define a set of standards and ### requirements for Eumetcal ### labellisation (beyond pilot ### phase) |  | Preliminary work by February 07 | Heikki |
| ### Develop competency ### Examination (depending on ### study above) |  | By March 07 (if work agreed) | Heikki |
| ### Train 1 central ‘assessor’ |  | By February 07 | Gordon |
| ## Monitor and evolve plan |  | As required | Carola |

# Note 1 – Contact COMET

COMET has delivered a distance learning training course in the week commencing 11 Sept. While the structure and external framework of the course is different to that of Eumetcal, there are nevertheless many lessons to learn from their experience. Additionally they are in the process of developing an Aviation Meteorology course and comparison of the syllabus would be very helpful and could save us some development time. Access to the appropriate sites in COMET has been acquired and discussions with COMET have started.

BoM are also very interested in our pilot and Jeff Wilson has offered to be involved and possible deliver a lecture, via internet, for some of our courses. Possibly the same with several European partners from Eumetcal (e.g. KNMI, as to be considered by Annemarie Braam, and Norway by Vibeke ...)

It is worth checking what is available from at least some of these sources very early in planning, i.e. before fixing the syllabus.

For later, both COMET and BoM would like to see how our pilots develop and to see any reports we produce. Additionally both have expressed a possible interest in enrolling a ‘silent’ member on our courses so that they can see the material and follow progress.

# Note 2 – Develop course material

This task is largely contained within Meteo France but has also to avoid a result which would appear as a fully French course. Timing is to MF’s internal requirements. However, background reading material and, possibly, material for the first phase of the course needs to be available by the middle of November (if possible) so that it can be placed on the web site and hence be available for students BEFORE the course starts. Remaining material can then follow but always it must be available a few weeks before it is required by the students so that there is time to place it on the web site before the relevant phase of the course is reached.

(If possible Jaakko might visit Toulouse between mid-October and mid-November, to enhance progress together with MF so that transfer of material from MF to the Eumetcal College site can be discussed and tested.

# Note 3 – Review of material / assistance from other NMSs

The Eumetcal SG wished for NMSs to have an input to the syllabus and 4-5 agreed to provide that input. However, to date, nothing has been received. For the Aviation Course there is only a little time for further consultation but that is not as critical since the syllabus is guided by WMO 258 Supplement 1 and hence there is less room for flexibility.

Nevertheless, KNMI, and possibly other NMSs, have an interest in either  participating in course delivery and/or reviewing the material as it is produced. MF need to bring this to a firm plan in time to include such help within the tight timetable.

It is logical for Christophe to handle the co-ordination with NMSs who are working actively on the syllabus and content. However, it is politically important that we receive significant contributions and, to obtain these, it may be useful for someone to help Christophe, specifically by chasing NMSs who are slower to respond.

# Note 4 – Web site development

The web site is already under development. It needs to be ready to incorporate the training material in December. But the web site does not need to be complete by then, it only needs to contain the aspects critical for the first pilot. Other aspects can be added later.

# Note 5 – Course delivery software

As a result of previous experiments it is more and more often agreed that Visit View is not sufficiently robust or capable of handling more that about 5-6 separate participating sites. There are difficulties with opening the necessary ports within the security framework of NMSs, interactive voice communication is fragile and in general it is probably too complex for non-experts to manage.

COMET has found the same issues and they used standard ‘internet meeting’ software and conference telephone links for their recent distance learning course. Eumetcal needs to make a decision on how the interactive internet sessions will be held and then to have and agreed solution in place by end Nov so that it can be tested thoroughly in December. It also has to consider, in due time, the consequences of this choice as to the way to insert, manage and even design the course material. A further aspect to consider is the cost of telephone links, especially for former Eastern Block countries – EUMETSAT have ideas here and may be able to help.

# Note 6 – Acquiring students

MF will need to write the course advertisement and disseminate it to appropriate NMSs by mid October at the latest. Critical here is the agreed course costs.

While there needs to be an equal opportunity for all to register on the course, there also needs to be some intervention to ensure firstly that there are an appropriate number (~16) for the pilot and also the right quality of student i.e. we need to manage expectations, for a pilot course. Since there is a limited time available the best way to handle this is to issue the advertisement in mid October and also approach NMSs directly to solicit applicants. It is suggested that a deadline for replies be set at 15 Nov and that would leave a month to intervene further, as necessary, depending on the response achieved by 15 Nov.

By working in this way we can simultaneously gain applicants through the advertisement and also supplement the list of applicants by invitation, if necessary and appropriate. We must also be prepared to turn some applicants down if there is a bigger response that we can handle.

It may go well and we may get a high response. But some contingency plans are required in case we need to encourage NMSs to send people on the first course.

# Note 7 – Certification

Certification was not approved by EUMETNET and so, at first impression, we should drop this topic.	 However, some members of Eumetcal would still like to see the College issue a pass certificate which is more meaningful that just a certificate of attendance. This note explores what could be achieved, within current resources. It is clear that EUMETNET are reading ‘certification’ as some form of official certificate ‘imposed’ on NMSs. In fact Eumetcal are more concerned with the internal college process. We will need to decide whether an internal pass ‘certificate’ is something which is internal to the college, and hence within our jurisdiction, or whether it contravenes the EUMETNET wish not to have any certification at all.

To date Eumetcal has explored the range of certification available, from a ‘certificate of attendance’ through to a fully legal certificate (or as near to it as possible throughout Europe). This is a complex issue and as we have explored it the following issues have emerged:

- There is concern that by certification we mean a legal certificate that all NMSs must use for all their staff. While this is NOT our intent there is always the danger that others (e.g. ICAO) would use our certification to impose this later.

- Many NMSs ‘fear’ certification that is influenced by EMS.

- EMS is concerned about the volume of work they would incur if they were associated with certification.

- NMSs fear that any current scheme that they are developing for SES may become invalid or seen to conflict with the College certification.

The challenge, if we decide to continue, is to develop a middle ground which is acceptable to EUMETNET and which supports NMSs efforts. One possibility for a middle ground position is the attached paper

in which we use ISO 9000 as the guiding influence on certification. In discussions with MeteoFrance it is possible that this middle ground involves a degree of formalisation of the EUMETCAL College as a “stand-alone” organisation that is beyond the requirement expressed by NMSs  As an alternative, the following approach could be followed:

- Use the ICAO – WMO documents (WMO 258 Supplement) as the base requirements.

- Develop a competency examination within Eumetcal.

- Add some limited quality control – e.g. use one central assessor to ensure a uniform “EUMETCAL” standard. Probably too early right now

- Issue internal Eumetcal certificate of ‘pass’.

The certificate would not state that a forecaster was fully compliant with WMO 258 Supplement but would state exactly what aspects the competency examination had covered leaving it to the NMS to cover aspects, such as special local features and compliance with the method of operation in force in a specific NMS. In this way the Eumetcal certificate would support a NMS in their efforts to comply with SES legislation.

This could be in place by the end of the Aviation course so that, if appropriate and timely, MeteoFrance could conduct the examination at the end of the course, while all the students are co-located – note that, because we are no longer dealing with a full certificate of competence, there is no longer the need for the examination to take place within the work place and it can now be conducted at any location able to simulate the basic conditions of a forecast office. However, it could also be omitted from the pilot and brought in on later courses. Since there is probably time to set up the procedures for the first pilot, the timings here are adjusted accordingly. But a slippage is easy to build in if events suggest this is beneficial.

Under this assumption, some preliminary thinking needs to be done before February 07 but the design of the examination need not be completed until nearer the end of the course. However, there are significant advantages in having a central assessor, largely because it will give Eumetcal knowledge and experience on which to develop ideas further;  it is probably sensible to train up one person in how to conduct competency exams. EUMETSAT have agreed to allow Gordon Bridge the time to train in this and, since costs are relatively cheap – less than €500 in total (figure to be confirmed) – that would be a prudent investment and should be done before February 07 so that Gordon can assist in any subsequent design of the examination. Without any central co-ordination there must be one focal point for the conduct of competency examinations and a central assessor provides that focus.

Depending on the success of that trial Eumetcal could then continue the discussion with EUMETNET to explore whether there is an acceptable position from which to progress, although this would be something for year 2 (or later) of the programme.

# Note 8 – Preliminary work on NMS course

While there was little success in gaining wider input to the syllabus of the Aviation Course, there is more time and more opportunity for NMSs to provide input to the NWP course.

# Note 9 – Contact with MET Alliance

The MET Alliance SG met at the end of August and expressed a keen interest to work with Eumetcal. Within Eumetcal we have a natural link person in AnneMarie Braam. However, while she can maintain the contact it would be time-consuming to brief her on all aspects of Eumetcal to the level necessary to open the conversation. It is therefore probably easier for someone with an existing knowledge of the development of Eumetcal to start a conversation with Nicole De Klerk to explore the opportunities for collaboration. AnneMarie may be able to attend that discussion.

MET Alliance are very interested in ‘certification’ (although this is probably more orientated to ‘organisational’ rather than ‘personal’ certification) and have in their mandate to explore certification for SES. When Eumetcal decides on how it will move forward on certification, a visit to Nicole would be very useful to start collaboration with MET Alliance. After that first contact, routine liaison can probably be achieved through AnnaMarie.